## BookedHours
CITS3200 Project Billed Hours Record for Zhichong Zhang(Terry) Each time you do some work on the project, note the week number, start and end date and hour, plus a brief description of the activity. At the end of each week send a copy of the sheet as it currently stands to your group's manager for recording on the group TimeSheet. Date in the form DD/MM/YY and time as XX:YY (24hr clock)
Wk | Begin |  | End |  | Activity | Session Hours | Total Hours
| Date | Time | Date | Time
2 | 2026-07-29 | 11:00 | 2026-07-29 | 12:00 | Attend weekly team meeting | 1 | 1 | 1
2 | 2026-07-30 | 14:00 | 2026-07-30 | 15:30 | Read project documentation and understand project requirement | 1.5 | 2.5 | 1.5
2 | 2026-07-31 | 14:30 | 2026-07-31 | 16:00 | Understand overall project workflow and system architecture | 1.5 | 4 | 1.5
3 | 2026-08-05 | 11:00 | 2026-08-05 | 12:00 | Attend weekly team meeting | 1 | 5 | 1
3 | 2026-08-06 | 10:00 | 2026-08-06 | 12:00 | Research Ubuntu 22 installation and project development environment | 2 | 7 | 2
3 | 2026-08-07 | 13:00 | 2026-08-07 | 15:00 | Review Sprint 1 requirements and work on project stories | 2 | 9 | 2
4 | 2026-08-12 | 11:00 | 2026-08-12 | 12:00 | Attend weekly team meeting and discuss sprint 1 deliverables | 1 | 10 | 1
4 | 2026-08-12 | 15:00 | 2026-08-12 | 16:00 | Review sprint 1 progess and gesture reconition requirements | 1 | 11 | 1
4 | 2026-08-15 | 10:00 | 2026-08-15 | 11:30 | Research MediaPipe for hand gesture reconition | 1.5 | 12.5 | 1.5
4 | 2026-08-16 | 16:00 | 2026-08-16 | 17:00 | Review gesture reconition approach and implementation plan | 1 | 13.5 | 1
5 | 2026-08-18 | 14:00 | 2026-08-18 | 16:00 | Set up and run the gesture recognition code in the local development environment | 2 | 15.5 | 2
5 | 2026-08-19 | 11:00 | 2026-08-19 | 12:00 | Attend weekly team meeting and discuss project progress | 1 | 16.5 | 1
5 | 2026-08-20 | 21:00 | 2026-08-20 | 23:00 | Conduct formal testing for predefined gestures and document testing results | 2 | 18.5 | 2
5 | 2026-08-19 | 13:00 | 2026-08-19 | 13:40 | Attend the client meeting | 0.66667 | 19.1667 | 0.66667
6 | 2026-08-26 | 11:00 | 2026-08-26 | 12:00 | Attend weekly team meeting | 1 | 20.1667 | 1
6 | 2026-08-26 | 12:00 | 2026-08-26 | 13:00 | Attend auditor meeting | 1 | 21.1667 | 1
6 | 2026-08-28 | 15:00 | 2026-08-28 | 16:30 | Attend the mentor meeting | 1.5 | 22.6667 | 1.5
7 | 2026-09-07 | 13:00 | 2026-09-07 | 15:00 | Modify react_to_gusture to support MP4 | 2 | 24.6667 | 2
7 | 2026-09-09 | 11:00 | 2026-09-09 | 12:00 | Attend weekly team meeting | 1 | 25.6667 | 1
7 | 2026-09-10 | 12:00 | 2026-09-10 | 13:00 | Run and debug react_to_gestures.py with MuJoCo simulation | 1 | 26.6667 | 1
7 | 2026-09-10 | 19:00 | 2026-09-10 | 21:30 | Conduct and document functional testing of simulation responses to recognized gestures | 2.5 | 29.1667 | 2.5
8 | 2026-09-14 | 15:00 | 2026-09-14 | 17:00 | Conduct updated MP4 gesture reaction testing in MuJoCo | 2 | 31.1667 | 2
8 | 2026-09-14 | 0.70833 | 2026-09-14 | 17:50 | Document and review updated gesture reaction testing results | 0.83333 | 32 | 0.83333
8 | 2026-09-16 | 11:00 | 2026-09-16 | 12:00 | Attend weekly team meeting and discuss project progress | 1 | 33 | 1
8 | 2026-09-16 | 13:00 | 2026-09-16 | 13:45 | Attend the client meeting | 0.75 | 33.75 | 0.75
9 | 2026-09-23 | 13:00 | 2026-09-23 | 13:40 | Attend the client meeting | 0.66667 | 34.4167 | 0.66667
9 | 2026-09-24 | 10:00 | 2026-09-24 | 11:00 | Review Project branches and prepare for merging | 1 | 35.4167 | 1
Wk | Begin |  | End |  | Activity | Session Hours | Total Hours | #VALUE!
| Date | Time | Date | Time |  |  |  | #VALUE!
9 | 2026-09-25 | 9:00 | 2026-09-25 | 9:45 | Attend the mentor meeting | 0.75 | 36.1667 | 0.75
9 | 2026-09-25 | 11:00 | 2026-09-25 | 12:00 | Attend auditor meeting | 1 | 37.1667 | 1
9 | 2026-09-26 | 10:00 | 2026-09-26 | 11:30 | Merge project branches in the required order, and Check the integrated project after merging | 1.5 | 38.6667 | 1.5
10 | 2026-09-30 | 11:00 | 2026-09-30 | 12:00 | Attend weekly team meeting | 1 | 39.6667 | 1
10 | 2026-09-30 | 14:00 | 2026-09-30 | 15:00 | Integrate GamepadBridge into SimController and update gesture_control.py | 1 | 40.6667 | 1
10 | 2026-09-30 | 15:00 | 2026-09-30 | 15:30 | Update the setup guide and push changes to Gesture-Branch-Cleanup | 0.5 | 41.1667 | 0.5
10 | 2026-10-02 | 10:00 | 2026-10-02 | 11:30 | Review project branches and begin the integration process | 1.5 | 42.6667 | 1.5
10 | 2026-10-03 | 18:30 | 2026-10-03 | 20:00 | Merging Project branches | 1.5 | 44.1667 | 1.5
11 | 2026-10-06 | 14:00 | 2026-10-06 | 15:30 | Set up and run the integrated gesture control system | 1.5 | 45.6667 | 1.5
11 | 2026-10-07 | 11:00 | 2026-10-07 | 12:00 | Attend weekly team meeting | 1 | 46.6667 | 1
11 | 2026-10-07 | 20:00 | 2026-10-07 | 22:00 | Conduct integration testing for gesture control and robot simulation | 2 | 48.6667 | 2
11 | 2026-10-08 | 15:00 | 2026-10-08 | 16:30 | Conduct integration testing for gesture control and robot simulation | 1.5 | 50.1667 | 1.5
11 | 2026-10-09 | 17:00 | 2026-10-09 | 17:35 | Attend the mentor meeting | 0.58333 | 50.75 | 0.58333
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Wk | Begin |  | End |  | Activity | Session Hours | Total Hours | #VALUE!
| Date | Time | Date | Time |  |  |  | #VALUE!
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Wk | Begin |  | End |  | Activity | Session Hours | Total Hours | #VALUE!
| Date | Time | Date | Time |  |  |  | #VALUE!
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0