## BookedHours
CITS3200 Project Billed Hours Record for Zhichong Zhang(Terry) Each time you do some work on the project, note the week number, start and end date and hour, plus a brief description of the activity. At the end of each week send a copy of the sheet as it currently stands to your group's manager for recording on the group TimeSheet. Date in the form DD/MM/YY and time as XX:YY (24hr clock)
Wk | Begin |  | End |  | Activity | Session Hours | Total Hours
| Date | Time | Date | Time
2 | 2026-07-29 | 11:00 | 2026-07-29 | 12:00 | Attend weekly team meeting | 1 | 1 | 1
2 | 2026-07-30 | 14:00 | 2026-07-30 | 15:30 | Read project documentation and understand project requirement | 1.5 | 2.5 | 1.5
2 | 2026-07-31 | 14:30 | 2026-07-31 | 16:00 | Understand overall project workflow and system architecture | 1.5 | 4 | 1.5
3 | 2026-08-05 | 11:00 | 2026-08-05 | 12:00 | Attend weekly team meeting | 1 | 5 | 1
3 | 2026-08-06 | 10:00 | 2026-08-06 | 12:00 | Research Ubuntu 22 installation and project development environment | 2 | 7 | 2
3 | 2026-08-07 | 13:00 | 2026-08-07 | 15:00 | Review Sprint 1 requirements and work on project stories | 2 | 9 | 2
4 | 2026-08-12 | 11:00 | 2026-08-12 | 12:00 | Attend weekly team meeting and discuss sprint 1 deliverables | 1 | 10 | 1
4 | 2026-08-12 | 15:00 | 2026-08-12 | 16:00 | Review sprint 1 progess and gesture reconition requirements | 1 | 11 | 1
4 | 2026-08-15 | 10:00 | 2026-08-15 | 11:30 | Research MediaPipe for hand gesture reconition | 1.5 | 12.5 | 1.5
4 | 2026-08-16 | 16:00 | 2026-08-16 | 17:00 | Review gesture reconition approach and implementation plan | 1 | 13.5 | 1
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Wk | Begin |  | End |  | Activity | Session Hours | Total Hours | #VALUE!
| Date | Time | Date | Time |  |  |  | #VALUE!
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Wk | Begin |  | End |  | Activity | Session Hours | Total Hours | #VALUE!
| Date | Time | Date | Time |  |  |  | #VALUE!
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Wk | Begin |  | End |  | Activity | Session Hours | Total Hours | #VALUE!
| Date | Time | Date | Time |  |  |  | #VALUE!
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0