## Sheet1
Risk No. | Title | Description | Severity | Likelihood | Mitigation
1 | Project Delay | Project deliverables may not be completed within the required timeframe, reducing the amount of functionality that can be demonstrated. | High | Moderate | Define clear milestones, prioritise minimum viable deliverables, review progress regularly, and maintain time for integration and testing.
2 | Limited Team Experience | Limited team experience with computer vision and robotics may lead to development delays, incorrect technical decisions, or additional rework. | High | High | Allocate time early for research and small prototypes, share technical knowledge within the team, and use established documentation and examples where possible.
3 | Integration Issues | Because the project is being developed by two groups, independently developed components may not integrate correctly or may use incompatible interfaces. | High | Moderate | Define common interfaces and data formats early, maintain consistent development environments, and perform regular integration tests throughout development.
4 | Gestures Not Specified | The seven required gestures are not yet fully defined, creating a risk that gestures will be ambiguous, visually similar, or interpreted differently by team members. | High | High | Define and document each gesture early, make gestures visually distinct from one another, and link each gesture to a specific robot action and acceptance test.
5 | Variation Between Users | Differences in height, body proportions, appearance, clothing, and movement style may reduce the accuracy of leader identification, gesture recognition, or motion mirroring. | Medium | High | Test the system with multiple participants and avoid tuning the system to a single person or body type.
6 | Motion-Capture Availability | Access to motion-capture equipment may be limited, reducing opportunities to collect ground-truth data for evaluating motion mirroring. | High | Moderate | Plan motion-capture sessions in advance and ensure the motion-mirroring system can also be developed and evaluated using camera-based pose data.
7 | G1 Hardware Access | Access to the physical G1 robot may be limited, reducing the time available for hardware integration and final acceptance testing. | High | High | Complete as much development and testing as possible in simulation, book hardware access early, and prepare test procedures before each hardware session.
8 | Environmental Conditions | Changes in lighting, camera position, background, or visibility may reduce the reliability of person tracking and gesture recognition. | High | Moderate | Test under a range of realistic lighting, backgrounds, camera positions, and distances, and document the expected operating conditions.
9 | System Latency | Processing delays between detecting a movement or gesture and the robot responding may make following, gesture reactions, or motion mirroring noticeably inaccurate. | Medium | High | Set a measurable latency target, measure end-to-end response time during development, and simplify or optimise processing if the target is exceeded.
10 | Simulation-to-Real Differences | Differences between the simulated G1 model and the physical robot may cause behaviours that work in MuJoCo to perform differently on real hardware. | High | Moderate | Use an accurate G1 simulation model, keep simulation parameters consistent with the physical robot, and validate the same test scenarios on real hardware when access is available.