## Instructions
CITS 3200: Time Analysis Sheet. Semester 2 2008
GROUP 21
MEMBERS: Christo Wesseloo, Dhava Ahdi, Dylan Hu, Lithasa Munasinghe, Terry Zhang, Murphy Chen
GENERAL INFORMATION
This spreadsheet is designed to help your group keep track of the time you have spent on your project, what you have completed and the estimated time you still require to complete specific tasks in your project. Feel free to add tasks but do NOT remove any. Do NOT alter any cells which are coloured RED, or remove anything from the RESULTS worksheet (you may add to the results sheet if you wish)
GENERAL TASKS
The General Tasks tab records information on the time you spend on specific tasks such as research, learning tools (like Bugzilla) and Documentation
Fill in the total time your group wishes to spend on the project - the unit recommends 60hours per person, but some groups may wish to spend a different amount of time to this
You may add tasks to the list of tasks - when you add a task record the week number that you added it.
Feel free to change the team members responsible for tasks over the course of semester
Each week fill in the time your group has spent on each task and the estimate of the time remaining to complete the task
Fill in the A cell with the ACTUAL time your group spent on a task the past week
Fill in the E cell with the time you ESTIMATE is still needed to complete a task
When a task has been completed fill in the completed cell with the week number which you completed it in
REQUIREMENTS
This Requirements tab records information on the time you spend coding and testing a specific requirement
Fill in week added for new Requirements
Fill in Team members Responsible
Fill in the Difficulty
Fill in the Estimated time remaining for coding a requirement
Fill in the Actual time you spent on coding the requirement this week
Fill in the Estimated time remaining for testing a requirement
Fill in the Actual time you spent on testing the requirement this week
If you Drop a requirement fill in the week number
If you Complete a requirement fill in the week number
When you enter the clients value for requirements the spreadsheet will check that value sums to $100
PERPERSON
Each week fill in the total hours each of you have spent working on the project.
RESULTS
Provides summary statistics on your project, these values are all calculated. Please do NOT alter anything on this worksheet!
The Calculations that use deliverable A refer to week 4
The Calculations that use deliverable B refer to week 8
Suggested total time refers to the units guide of 60 hors per student per semester
Feel free to add any calculations that you feel will assist your group in tracking your progress
© 2006 Sarah Hatton and Richard Thomas. School of Computer Science and Software Engineering UWA

## General Tasks
To Do:
Fill in the total hours your group has allocated for the project
Fill in week added for new tasks
Fill in Team members Responsible
Fill in the Estimated time remaining on a task (E)
Fill in the Actual time you spent on a task for that week (A)
If you complete a task fill in the week number
Total Hours our group has allocated = |  | 360
Task |  |  | Time Estimate (hrs) (E=Estimated time remaining, A=Actual time spent this week)
Task Name | Week Added | Team Members Responsible | week 2 |  | week 3 |  | week 4 |  | week 5 |  | week 6 |  | week 7 |  | week 8 |  | week 9 |  | week 10 |  | week 11 |  | Completed
|  |  | E | A | E | A | E | A | E | A | E | A | E | A | E | A | E | A | E | A | E | A | (Week Number)
Learning Techniques and tasks (eg bugzilla and CVS) | 0
Research and Investigation | 2 | ALL team members | 44 | 6.5 | 37.25 | 6.75 | 35 | 6.5 |  |  | 35 |  | 35
Requirements Gathering | 0
Requirements Analysis | 0
System Design | 4 | [5 empty] | 100 | 2.75 | 40 | 12 | 40 |  | 40
Test Design | 0 | [7 empty] | 5 | 3 | 5 |  | 5
Documentation | 2 | Project Manager | 20 | 1.5 | 18 | 1.75 | 17 | 1.75 | 15 | 1.75 | 15 | 1 | 15 | 1.25
Project Meeting and Communication | 2 | ALL team members | 60 | 6 | 54 | 6 | 40 | 6 | 40 | 6 | 40 | 15.33 | 40 | 5.25
Review | 0
Weekly Client Meetings | 2 | Team Members who need to attend | 60 | 4 | 55.5 | 4.5 | 35 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0
Sprint 1 Deliverables | 2 | ALL team members |  |  | 12 | 7.25 | 0 | 7.75 | [14 empty] | 4
Dependency Installation | 3 | ALL team members |  |  | 10 | 1.5 | 3 | 5.75 |  |  | 3 |  | 3
Simulation Environment (MuJoCo) | 7 | Christo, Dhava, Murphy | [10 empty] | 20 | 16.83
TOTAL

## Requirements
To Do:
Fill in week added for new Requirements
Fill in Team members Responsible
Fill in how difficult you think it will be
Fill in the Estimated time remaining for coding a requirement (CE)
Fill in the Actual time you spent on coding the requirement this week (CA)
Fill in the Estimated time remaining for testing a requirement (TE)
Fill in the Actual time you spent on testing the requirement this week (TA)
If you Drop a requirement fill in the week number
If you Complete a requirement fill in the week number
The cell below checks that your Value sums to $100
Requirement Name | Week Added | Team Members Responsible | Client Value ($) | Time (CE = Code Estimated Time Remaining, CA = Actual Time Spent Coding This Week, TE= Testing Estimated Time Remaining, TA= Actual Time Spent Testing This Week) | [41 empty] | difficulty
|  |  |  | Week 2 |  |  |  | Week 3 |  |  |  | Week 4 |  |  |  | Week 5 |  |  |  | Week 6 |  |  |  | Week 7 |  |  |  | Week 8 |  |  |  | Week 9 |  |  |  | Week 10 |  |  |  | Week 11 |  |  |  | dropped (week) | completed (week) | 1-easy 2-medium 3-hard
|  |  |  | CE | CA | TE | TA | CE | CA | TE | TA | CE | CA | TE | TA | CE | CA | TE | TA | CE | CA | TE | TA | CE | CA | TE | TA | CE | CA | TE | TA | CE | CA | TE | TA | CE | CA | TE | TA | CE | CA | TE | TA
Gesture Recognition Program | 3 | Christo, Murphy, Terry |  | Week 3 CE: 25; Week 3 CA: 0; Week 3 TE: 5; Week 3 TA: 0; Week 4 CE: 20; Week 4 CA: 1; Week 4 TE: 5; Week 4 TA: 0; Week 5 CE: 20; Week 5 CA: 8.5; Week 5 TE: 10; Week 5 TA: 5.75; Week 6 CE: 10; Week 6 CA: 0; Week 6 TE: 2; Week 6 TA: 0; Week 7 CE: 10; Week 7 CA: 6.5; Week 7 TE: 2; Week 7 TA: 4.5 |  |  | 2
Person Tracking and Recognition Program | 3 | Dylan, Lithasa, Dhava |  | Week 3 CE: 25; Week 3 CA: 0; Week 3 TE: 5; Week 3 TA: 0; Week 4 CE: 20; Week 4 CA: 0; Week 4 TE: 5; Week 4 TA: 0; Week 5 CE: 20; Week 5 CA: 2.75; Week 5 TE: 5; Week 5 TA: 1.5; Week 6 CE: 10; Week 6 CA: 0; Week 6 TE: 2; Week 6 TA: 1; Week 7 CE: 10; Week 7 CA: 3; Week 7 TE: 2; Week 7 TA: 0 |  |  | 2
TOTAL

## PerPerson
TO DO:
Each week fill in the total hours each of you have spent working on the project.
Total Hours
Name | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8 | week 9 | week 10 | week 11 | TOTAL
Christo Wesseloo | 5 | 5.5 | 5 | 7.75 | 2 | 8.5
Dhava Ahdi | 1.75 | 3.5 | 4 | 3 | 3 | 10.83
Dylan Hu | 1.75 | 3.75 | 6.75 | 5.5 | 3.5 | 3.25
Lithasa Munasinghe | 1.75 | 3.25 | 6 | 6 | 2 | 2.5
Terry Zhang | 4 | 5 | 4.5 | 5.6 | 3.5 | 6.5
Murphy Chen | 3 | 6.5 | 5 | 7.8 | 2.33 | 5.75

## Results
TOTAL TIME SPENT |  |  | CALCULATIONS
Suggested Total Time to be spent by group = | (Computed as 60 hours per person) |  | MET | SCRUBBED
Actual Total Time Spent By Group =
Hours Remaining From Suggested Time Budget =
Hours Remaining From Your Groups Chosen Time Budget =
Initial Time Estimate compared to Actual Time Spent = |  | (Taken from week 4)
Initial Time Estimate compared to Actual Time Spent = |  | (Taken from week 8)
REQUIREMENTS
Number of Requirements Met =
Value of Requirements Met =
Number of Requirements Scrubbed =
Value of Requirements Scrubbed =
TASKS
Number of Tasks Completed =
Number of Tasks Remaining =